## SUMMARY
STEAMEE — KPI Framework Change Log ¦ Analysis & Decision Record
CHANGE SUMMARY
| Category | Count | Impact
| 🟢 NEW KPIs Added | 11 | Covers gaps: workforce, inventory, slots, community, subscription
| 🔵 KPIs Updated / Renamed | 9 | Formula clarified, source fixed, or scope expanded
| 🔴 KPIs Removed / Merged | 6 | Duplicates eliminated — data fed to single canonical KPI
| ⚠️ KPIs Flagged (Data Not Ready) | 7 | Blocked by known data gaps — marked for Phase 2
| TOTAL KPIs in Framework | 59 | Up from original 45 — within 50-60 target range
CRITICAL FINDINGS FROM PORTAL AUDIT
| Bug #1 | other_orders = -151 | Order count arithmetic bug in Analytics API — produces negative values
| Bug #2 | revenueDashboard no-date filter | Revenue API returns ₹0 for all metrics when no date range passed — misleading zeros
| Bug #3 | Order Reviews page | Hard SQL error — page completely broken, must be fixed before Metabase views built on this table
| Bug #4 | Dashboard filter 500 error | Main dashboard filter returns 500 Internal Server Error — all date-range KPIs on homepage are blind
| Gap #1 | marketing_spend table missing | CAC (Q22) cannot be computed — no channel-level spend tracked. Phase 2 dependency.
| Gap #2 | Push notification tracking absent | Campaign effectiveness KPIs blocked. MoEngage integration will fix this.
| Gap #3 | Razorpay reconciliation broken | Payment data join to order_id is unreliable — Razorpay Capture Rate (Q33) may be inaccurate
| Gap #4 | Pressman payout needs formatting | Ironer Payout Accuracy KPI (NEW) cannot be automated until payout table is structured
DUPLICATION MATRIX (what was consolidated)
| Duplicate Group | Appeared On | Decision
| Total Revenue | Dashboard + Revenue Dash + Rev&Ops Hub | KEEP on Rev&Ops Hub. Summary card only on others.
| Avg Order Value | Dashboard + Finance + Operations | KEEP in Finance (Q30). Remove from others.
| Active/Churned Users | Dashboard + User Analytics + User Returning | KEEP in User Segment Analytics. Dashboard shows headline count only.
| Cohort / Returning | Cohort page + User Returning page | MERGE User Returning INTO Cohort page. Single source.
| Complaint Analytics | Dashboard tab + Complaint Management | MOVE to Complaint Management. Dashboard shows summary card only.
| ZoneWise Report | Reports + Logistics + Operations sidebar | KEEP in Reports. Remove redundant sidebar entries.
EXISTING PORTAL KPI MAPPING
| Portal Status | Count | Meaning
| 🟢 PORTAL-USE | 24 | KPI already surfaced in existing portal — can use data directly
| 🟡 PORTAL-ADAPT | 23 | Portal has partial data — needs Metabase formula or aggregation
| 🔴 PORTAL-SKIP | 12 | Not in any portal page — full Metabase query from scratch
| KEY INSIGHT: |  | Of 59 KPIs mapped: 24 already have usable portal data, 23 need adaptation, 12 need to be built from scratch. Prioritise PORTAL-USE KPIs for fast Metabase deployment (< 1 sprint).
| TOP PORTAL ASSETS: |  | Ironer Performance Report (Q9b) ¦ Ironer Attendance Report (Q18a) ¦ Complaint Refund Report (Q34) ¦ Onboarding Report (Q24) ¦ Cohort Analysis (Q21) ¦ Audit Dashboard (Q45a) ¦ Wallet Overview (Q36a)

## KPI MASTER LIST
Q# | Dashboard | KPI Name | Status | Change Type | Plain-English Metabase Question | Source View / Table | Formula / Logic | Data Ready? | Alert Threshold | Owner | Why Changed | Existing Portal Page | Portal Status | Portal Notes
Q1 | Operations | On-Time Pickup Rate | KEEP | — | Show % of orders where pickup_sla_met=true, by zone_id and day, last 30 days. Line chart. | v_sla_tracking | COUNT(pickup_sla_met=true)/COUNT(*) × 100 | YES | 🔴<80% 🟡80–90% 🟢>90% | Operations Head | Core SLA metric. Pickup TAT = ≤2 hrs. Unchanged. | Analytics → Detail TAT Analytics Store-wise TAT Performance chart shows success vs breach per store | PORTAL-ADAPT | TAT page shows success/breach bars per store — this can be adapted. But it's breach count not %; need to compute % in Metabase.
Q2 | Operations | On-Time Ironing Rate | KEEP | — | Show % of orders where ironing_sla_met=true, by zone_id, last 30 days. | v_sla_tracking | COUNT(ironing_sla_met=true)/COUNT(*) × 100 | YES | 🔴<85% 🟡85–95% 🟢>95% | Operations Head | Ironing TAT = ≤12 hrs from received_at store. | Analytics → Detail TAT Analytics Ironer Efficiency (Avg TAT Hours) chart + Ironer TAT & Volume Explorer table | PORTAL-ADAPT | Portal shows Avg TAT hours per ironer — good for drill-down. Ironing Pending trend also available. Needs % computation in Metabase.
Q3 | Operations | On-Time Delivery Rate | KEEP | — | Show % of orders where delivery_sla_met=true, by zone_id and day. | v_sla_tracking | COUNT(delivery_sla_met=true)/COUNT(*) × 100 | YES | 🔴<85% 🟡85–92% 🟢>92% | Operations Head | Delivery TAT = ≤4 hrs from ironing done. | Analytics → Detail TAT Analytics Delivery Pending Trend chart | PORTAL-ADAPT | Delivery Pending Trend is count of pending — not delivery rate %. Use as leading indicator in portal; compute rate in Metabase.
Q4 | Operations | End-to-End TAT (Avg Hours) | KEEP | — | Show AVG total_tat_hours per zone per week for last 8 weeks. Grouped bar chart. | v_sla_tracking ALSO: /api/getOrdersTATData confirmed — returns total_monitored, ironing_pending, pickup_pending, delivery_pending in real-time | AVG(TIMESTAMPDIFF(HOUR, order_placed_time, deliver_time)) per zone per week | YES | 🔴>20hrs 🟡16–20hrs 🟢<16hrs | Operations Head | Combines all 3 SLA stages into one end-customer experience metric. | Analytics → Detail TAT Analytics Total TAT card (52 orders, ↑100%) + Ironer TAT & Volume Explorer | PORTAL-ADAPT | Portal shows Total TAT count (52 pending). Ironer TAT Explorer shows per-ironer avg TAT (e.g. Kala=13h, jeremy=20h). Good source. Metabase to aggregate by zone. BALA AUDIT: /api/getOrdersTATData confirmed working from Dashboard > Revenue & Ops Hub. Returns real-time pending counts by stage. Use for live TAT monitoring card alongside historical avg calculation.
Q5 | Operations | Cancelled Order Rate | KEEP | — | Show total_orders and cancelled_orders by zone by week. KPI card with cancellation %. | v_daily_store_summary | COUNT(cancel_status=1)/COUNT(*) × 100 | YES | 🔴>8% 🟡5–8% 🟢<5% | Operations Head | cancel_status=1 confirmed in API. | Analytics → Detail Order Analytics Order Lifecycle Segments: Cancelled card (count + % change vs prior) | PORTAL-USE | Cancelled card directly on Order Lifecycle Segments. Confirmed working. Use as-is for portal. Metabase builds the % rate formula.
Q6 | Operations | Order Transfer Rate | KEEP | — | Show orders where order_transfer=1, by zone_id and week. As % of total zone orders. | orders table | COUNT(order_transfer=1)/COUNT(*) × 100 per zone per week | YES | 🔴>5% 🟡2–5% 🟢<2% | Operations Head | High transfer rate = capacity mismatch between zones. | Not directly visible in portal UI — order_transfer is a DB field only | PORTAL-SKIP | No portal page surfaces order transfers. Metabase query needed directly on orders table.
Q7 | Operations | Damage Rate | KEEP | — | Show orders where is_damaged_ironing≠0, as % of completed, by zone and month. | orders table | COUNT(is_damaged_ironing≠0)/COUNT(delivered) × 100 | YES | 🔴>1% 🟡0.5–1% 🟢<0.5% | Operations Head | is_damaged_ironing field confirmed in API response. | Complaint Analytics → Most Complained Ironers (by ticket volume) Complaint Categories: Ironing (25 tickets May, 48 April) | PORTAL-ADAPT | Complaint page shows Ironing category ticket count and Most Complained Ironers table. Use as proxy for damage rate drill-down. Actual damage flag must come from orders table.
Q8 | Operations | Clothes Count Accuracy | KEEP | — | Show % of orders where vendor_check_quantity matches quantity, by zone. | orders table | COUNT(vendor_check_quantity=quantity)/COUNT(completed) × 100 | YES | 🔴<95% 🟡95–98% 🟢>98% | Operations Head | Quantity mismatch is root cause of most damage and missing-clothes complaints. | Reports → Ironer Summary Report vendor Cloth Quantity vs Customer Cloth Quantity columns in table | PORTAL-ADAPT | Ironer Summary Report has 'Customer Cloth Quantity' vs 'Vendor Cloth Quantity' columns — this is the direct source for count accuracy. Adapt this table for the KPI formula.
Q9 | Operations | Active Orders (Live Count) | KEEP | — | Show live count of orders where order_status≠Completed and cancel_status=0, by zone_id. | orders table — real-time | COUNT(*) WHERE cancel_status=0 AND status NOT IN (delivered, cancelled) | YES | N/A — live ops view | Store Manager | Real-time operational pulse. API confirmed working. | Analytics → Order Lifecycle Segments (main dashboard) Upcoming, Received, In Progress, Ironing, Completed cards all live | PORTAL-USE | Order Lifecycle Segments panel on Analytics dashboard is exactly this — live counts by lifecycle stage. Already working. Portal shows Upcoming=—, Received=—, In Progress=—, Ironing=—. Use directly.
Q9a | Operations | Slot Utilisation Rate | NEW | ADD | Show COUNT orders per pickup slot vs total slot_count capacity, by zone and day. Heatmap. | orders + timeslot_assign table | COUNT(orders per slot)/slot_count × 100 per zone per slot | YES | 🔴<40% 🟡40–70% 🟢>70% | Operations Head | Slot data is live (TimeSlot API confirmed). Heatmap reveals peak demand — drives rider pre-positioning. | Time Management → TimeSlot Assign Timeslot Management Filter Timeslot Calendar shows availability data | PORTAL-ADAPT | TimeSlot Assign page has a calendar view showing slot availability. But it shows capacity not utilisation rate. Metabase to compute utilisation from orders vs slot capacity.
Q9b | Operations | Pressman Productivity Score | NEW | ADD | Show per-ironer: clothes ironed per shift / (shift_hours × benchmark). Ranked efficiency table. | ironer_performance_analytics API (/api/ironer-performance-analytics) Confirmed fields: total_qty, total_defects, avg_efficiency, total_orders | (vendor_iron_quantity per ironer per day)/(shift_hours × benchmark_per_hour) × 100 | YES | 🔴<60% 🟡60–80% 🟢>80% | Operations Head | Ironer Performance Report API confirmed working — returns qty, defect%, avg time, efficiency. | Reports → Ironer Performance Report Cards: Total Clothes, Total Orders, Avg Time/Order, Avg Efficiency Table: Ironer, Qty, Orders, Defect Qty, Defect%, Avg Time, Efficiency | PORTAL-USE | CONFIRMED: /api/ironer-performance-analytics returns avg_efficiency directly (sample: 20). Also has total_qty (clothes), total_defects, total_orders. Pressman scorecard fully computable. Note: payout_per_cloth not yet in API — mark as Phase 2 cost component.
Q9c | Operations | Inventory Stock-Out Alerts | NEW | ADD | Show count of unread low-stock notifications by store. Alert badge. | inventory/notifications/low_stock API | COUNT(low_stock notifications where is_read=0) per store | YES | 🔴Any unread = RED | Store Manager | Low-stock notification API confirmed in portal audit. | Operation Management → Audit Dashboard Open Issues card (82 open), Inventory tab | PORTAL-USE | Operation Management Audit Dashboard has Inventory tab and Open Issues count (82 open). Use this directly. Already surfaces stock alerts. Metabase adds trending.
Q10 | Logistics | Rider Utilisation Rate | UPDATE | FORMULA FIX | Show active task hours vs total shift hours per rider per week. Use Rider Performance Report. | orders + rider_performance_analytics API (/api/rider-performance-analytics) Confirmed: 24 riders, 2225 orders, avg_delivery_time=136.8 min, total_distance=3772.81 km | SUM(active_task_hours)/SUM(shift_hours) × 100 per rider per week | YES | 🔴<50% 🟡50–70% 🟢>70% | Logistics Head | Source fixed: use Rider Performance Report API (confirmed). Not timestamp spans. | Reports → Rider Performance Report Cards: Active Riders, Total Orders, Avg Delivery, Total Distance Table: Rider, Mobile, Orders, Avg Time, Fastest, Slowest, Distance | PORTAL-USE | CONFIRMED: /api/rider-performance-analytics returns total_riders, total_orders, total_distance, avg_delivery_time directly. Use avg_delivery_time field for utilisation proxy. Bala SR audit: 24 riders, 2225 orders confirmed.
Q11 | Logistics | Pickup Acceptance Rate | KEEP | — | Show % of orders where TIMESTAMPDIFF(MINUTE, created_at, pickup_accept_time) ≤ 15 mins, by zone and week. | orders table | COUNT(pickup_accept_time−created_at ≤ 15min)/COUNT(orders) × 100 | YES | 🔴<70% 🟡70–85% 🟢>85% | Logistics Head | pickup_accept_time confirmed in orders table. | Analytics → Detail TAT Analytics Upcoming Pending Trend + Store-wise TAT Performance | PORTAL-ADAPT | Upcoming Pending (42, ↑100%) shows pickups not yet accepted. Store-wise TAT breach chart covers this partially. Metabase computes the ≤15min acceptance rate properly.
Q12 | Logistics | Deliveries Per Rider Per Day | KEEP | — | Show COUNT completed deliveries by drop_runner and DATE(deliver_time). Avg across active riders. | orders table | COUNT(completed deliveries)/COUNT(active_riders) per day per zone | YES | 🔴<4 🟡4–6 🟢>6 | Logistics Head | drop_runner and deliver_time confirmed in API response. | Reports → Rider Performance Report Table: Rider → Orders column (deliveries per rider) | PORTAL-USE | Rider Performance Report table shows Orders per Rider. Already filterable by date range. Use directly. Add zone breakdown in Metabase.
Q13 | Logistics | COD Collection Rate | UPDATE | SOURCE FIX | Show % of orders where payment_mode='Cash' AND DeliverySuccess=1, by zone and week. | orders table | COUNT(payment_mode='Cash' AND DeliverySuccess=1)/COUNT(payment_mode='Cash') × 100 | YES | 🔴<90% 🟡90–96% 🟢>96% | Logistics Head | CRITICAL FIX: field value is 'Cash' not 'COD'. | Revenue Dashboard → COD Revenue card Analytics → Online vs COD Order Trend + Online vs COD Revenue Trend charts | PORTAL-ADAPT | Revenue Dashboard shows COD Revenue (₹2,33,646) and Online Revenue (₹4,692). COD vs Online trend charts exist. But collection rate (% successfully collected) is not computed — Metabase adds this.
Q14 | Logistics | Zone SLA Breach Rate | KEEP | — | Show % of orders per zone where ANY SLA flag = false. | v_sla_tracking | COUNT(any SLA flag=false)/COUNT(total) × 100 per zone | YES | 🔴>15% 🟡8–15% 🟢<8% | Logistics Head | Composite SLA breach — any failure in pipeline counts. | Analytics → Detail TAT Analytics Store-wise TAT Performance: Success vs Breach bars per store | PORTAL-ADAPT | Store-wise TAT Performance chart shows breach vs success per store — this is very close to Zone SLA Breach Rate. But breach count not %. Metabase computes the %.
Q15 | Logistics | Rider-Caused Delay Rate | UPDATE | THRESHOLD UPDATE | Show orders where pickup_minutes>120 OR delivery_minutes>240, as % of TOTAL orders (not just breached), by zone. | v_sla_tracking | COUNT(pickup_min>120 OR delivery_min>240)/COUNT(total_orders) × 100 | YES | 🔴>10% 🟡5–10% 🟢<5% | Logistics Head | Denominator changed to total orders — honest rate vs breached-only (misleading). | Analytics → Detail TAT Analytics Pickup Pending (42 orders) + Delivery Pending (10 orders) cards | PORTAL-ADAPT | Pending counts in portal are real-time but not computed as % of total orders. Metabase computes the rate. Portal cards are good operational alerts.
Q16 | Logistics | OTP Compliance Rate | KEEP | — | Show % of pickup orders where pick_otp verified (≠0) and delivery orders where del_otp verified. | orders table | COUNT(pick_otp≠0)/COUNT(pickup_orders) × 100 | YES | 🔴<95% 🟡95–98% 🟢>98% | Logistics Head | pick_otp and del_otp confirmed in API response. | Not surfaced in any portal page — DB field only | PORTAL-SKIP | OTP fields exist in DB but no portal page reports on OTP compliance. Full Metabase query needed.
Q17 | Logistics | Order Retrigger Rate | KEEP | — | Show % of orders where retrigger_pick_order_id IS NOT NULL, by zone and month. | orders table | COUNT(retrigger_pick_order_id IS NOT NULL)/COUNT(total) × 100 | YES | 🔴>5% 🟡2–5% 🟢<2% | Logistics Head | retrigger_pick_order_id confirmed in API response. | Analytics → Order Lifecycle Segments RTO Retrigger card (count + % change) | PORTAL-USE | RTO Retrigger card is on the Order Lifecycle Segments panel. Confirmed on dashboard. Use this for the count. Metabase computes the % rate.
Q18 | Logistics | Avg Pickup-to-Store Time | UPDATE | DEPENDENCY NOTE | Show AVG(TIMESTAMPDIFF MINUTE, picked_up_time, deliveryto_ven_time) by zone/week. BLOCKED pending DATETIME fix. | orders table (after DATETIME fix) | AVG(TIMESTAMPDIFF(MINUTE, picked_up_time, deliveryto_ven_time)) per zone per week | PARTIAL | 🔴>90min 🟡60–90min 🟢<60min | Logistics Head | picked_up_time NULL in most records. Tech must fix DATETIME population first. | Reports → Rider Performance Report Avg Time column per rider (total avg delivery time) | PORTAL-ADAPT | Rider Performance Report shows Avg Time per rider — this covers avg delivery time. But pickup-to-store specifically (the transit leg) requires picked_up_time fix in DB.
Q18a | Logistics | Rider Attendance Rate | NEW | ADD | Show % of scheduled riders checked in on time per day, by zone. | attendance_analytics API (/api/attendance-analytics) Confirmed fields: total_sessions, completed_sessions, active_sessions, avg_duration_minutes | COUNT(riders checked in)/COUNT(scheduled) × 100 per day per zone | YES | 🔴<70% 🟡70–85% 🟢>85% | Logistics Head | Attendance Report confirmed: 33% avg attendance rate visible. Rider no-show = direct SLA breach cause. | Reports → Ironer Attendance Report Cards: Total Sessions, Active Now, Avg Duration Ledger: Avg Attendance 33%, Total Present 184, Total Absent 366, Total Hours 1707h | PORTAL-USE | CONFIRMED: /api/attendance-analytics returns total_sessions, completed_sessions, active_sessions, avg_duration_minutes (sample: 347 min). Rider Attendance Rate = completed_sessions/total_sessions × 100. Filters: vendor_id, zone_id, ironer_id, date range.
Q19 | Growth | Monthly Active Users (MAU) | KEEP | — | Show COUNT DISTINCT user_id with order in current + last 6 months. Bar chart with MoM % change. | orders table | COUNT(DISTINCT user_id WHERE created_at >= DATE_SUB(NOW(), INTERVAL 30 DAY)) | YES | Alert if MoM growth < 5% | CMO | 30-day window for MAU = industry standard. | Analytics → User Segment Analytics Cards: Total Users 599 ↑15%, Active 3 ↓91.9%, Inactive 92 ↑39.4% | PORTAL-USE | User Segment Analytics panel on dashboard shows Active, Inactive counts with % change. Active Users card directly. Detailed User Growth page has User Retention & Status Trend chart. Use both. BALA AUDIT: /api/user-analytics confirmed. Returns: total_users, active_users, with_address, feedback_given. Sample: total_users=89, active_users=38 (43% active rate). Filter by date range, zone_id, user_status, user_type.
Q20 | Growth | New Customer Acquisition | KEEP | — | Show users whose first order falls in each month. Line chart. | orders table | COUNT(DISTINCT user_id WHERE MIN(created_at) = current_month) per month | YES | Alert if MoM new user growth <0% | CMO | Renamed from 'New Customers' — 'Acquisition' signals the action. | Analytics → User Growth Details New User Registration Trend chart (Day/Week/Month/Year) User Segment: Onboarded 342 ↑44.9% | PORTAL-USE | New User Registration Trend chart exists in User Growth Details. Onboarded card (342, ↑44.9%) is the headline count. Use directly. Metabase adds cohort month breakdown. BALA AUDIT: /api/user-analytics confirmed. Returns: total_users, active_users, with_address, feedback_given. Sample: total_users=89, active_users=38 (43% active rate). Filter by date range, zone_id, user_status, user_type.
Q21 | Growth | 30-Day Repeat Order Rate | KEEP | — | Show % of users per cohort month who placed 2nd order within 30 days of first. | orders: user_id, created_at | COUNT(users with 2nd order within 30d of 1st)/COUNT(cohort_users) × 100 | YES | 🔴<20% 🟡20–35% 🟢>35% | CMO | D2C service benchmark: 25–40% repeat in 30d. | Dashboard → Cohort Analysis User Retention Cohort table: Apr 2026=459 users, 23.7% returned next month Retention & Repeat Customer Rate chart | PORTAL-USE | ✅ BEST PORTAL ASSET: Cohort Analysis page has User Retention Cohort table with exact monthly retention % (Apr 2026: 23.7% returned, 7.2% two months later). Retention & Repeat Customer Rate chart also available. Use directly.
Q22 | Growth | CAC by Channel | FLAG | DATA GAP | BLOCKED: marketing_spend table doesn't exist. Phase 2. | orders + marketing_spend (FUTURE) | Total Marketing Spend per channel / COUNT(new customers via channel) | NO | Channel-specific targets once data available | CMO | No channel-level spend tracked in any system. Phase 2 dependency. | Offers → Promocode, Cashback, Voucher pages Reports → Offer Report (Promo + Cashback usage data) | PORTAL-SKIP | Portal has promo/cashback usage (cost side) but NO marketing spend data (investment side). CAC is impossible without spend. Flag for Phase 2.
Q23 | Growth | Promo ROI | UPDATE | FORMULA EXPANDED | Show SUM(order_amount) and SUM(ALL 5 discount fields) for promo orders by month. Net Revenue Retained = order_amount − all discounts. | orders table | SUM(wallet_used+promocode_used+cashback_used+voucher_used+coins_used) vs SUM(order_amount) | YES | 🔴discount >25% of revenue 🟢<15% | CMO | Original only counted promocode_used. All 5 discount fields confirmed. | Reports → Offer Report (Promocode & Cashback Report) Table: Promocode, Order Amount, Promo Discount, Payable, Zone Offers → Voucher → Usage Log: Discount Applied, Redeemed At | PORTAL-USE | Offer Report shows Promo Discount and Payable per order. Voucher Usage Log shows discount applied per voucher. Use both tables. Metabase aggregates all 5 discount types together for true total. BALA AUDIT CONFIRMED: /api/promo-analytics?type=promocode returns summary: total_uses, total_discount, total_order_amount. Sample: 10 uses, ₹660 discount, ₹2580 order_amount. Promo ROI = (total_order_amount - total_discount) / total_discount. Supports both type=promocode and type=cashback.
Q24 | Growth | App Funnel Conversion Rate | UPDATE | SOURCE CLARIFIED | Show registered → address → bag → cloth → order funnel. Use Onboarding Report API. | user_analytics API (/api/user-analytics) Confirmed: total_users, with_address, active_users, feedback_given, conversion_rate field directly in summary | Cloth_Order_Placed/Total_Registered × 100 (from onboarding summary) | YES | 🔴<10% 🟡10–25% 🟢>25% | CMO | Onboarding Report API returns conversion_rate directly. | User Management → Onboarding Report Cards: Total Registered, Added Address, Bag Order Placed, Cloth Order Placed, Conversion Rate, Feedback Given Filters: Zone, User Status, User Type, TeleCaller Status, Date range | PORTAL-USE | CONFIRMED: /api/user-analytics?from_date=X&to_date=X&zone_id=X returns summary.conversion_rate directly. No manual calculation needed — use API field. Also returns: total_users=89, with_address=89, active_users=38 in sample. Filters: zone_id, user_status, user_type, filter_mode.
Q25 | Growth | Smart Bag Utilisation Rate | UPDATE | RENAME + FORMULA FIX | Show bag_buy=1 users with cloth order in last 30 days, as % of all bag_buy=1 users. | users + orders | COUNT(bag_buy=1 with cloth order in 30d)/COUNT(bag_buy=1) × 100 | YES | 🔴<40% 🟡40–60% 🟢>60% | CMO | Renamed to 'Smart Bag'. Fixed: cloth order not any order. | User Management → Onboarding Report Bag Order Placed card + Cloth Order Placed card — gap between them = unactivated bag users | PORTAL-ADAPT | Onboarding Report shows Bag Order Placed vs Cloth Order Placed counts. Gap = bag owners not ordering clothes. Use this as proxy in portal. Exact utilisation rate needs Metabase query on users+orders join.
Q26 | Growth | Churn Rate | UPDATE | WINDOW ALIGNED | Show users with ≥1 order whose last order >60 days ago, as % of total users with any order. | cohort_analytics API (/api/cohort-analytics) Confirmed: stats.total, stats.returning, stats.non_returning, stats.retention_percentage | COUNT(MAX(created_at) < NOW()−60d)/COUNT(users_with_orders) × 100 | YES | 🔴>15% 🟡8–15% 🟢<8% | CMO | 60-day window = MoEngage trigger window per scope doc. | Analytics → User Growth Details Churned User Personas chart (users with no orders in 30 days, by loyalty tier) User Segment: Churned 0 ↓100%, Inactive 92 ↑39.4% | PORTAL-USE | CONFIRMED: /api/cohort-analytics?from_month=X&to_month=X&type=returning returns retention_percentage directly (sample: 100%). Churn Rate = 100 - retention_percentage. Filters: zone_id, user_status, user_type. NOTE: Sample shows 19 users, 19 returning, 0 non-returning — data may be filtered to active zone only.
Q27 | Growth | Promo-to-Organic Retention Rate | UPDATE | RENAME | Show users who used promo on order 1 and placed order 2 with NO promo within 30 days. | orders: user_id, promocode_used, created_at | COUNT(order1 promo AND order2 no-promo within 30d)/COUNT(promo_users) × 100 | YES | 🔴<15% 🟡15–30% 🟢>30% | CMO | Renamed from 'Promo-to-Retention Ratio'. Measures habit formation post-promo. | Reports → Offer Report Promocode Report + Cashback Report (per-user promo usage with Order ID) | PORTAL-ADAPT | Offer Report has per-user promo usage with Order ID — can trace user's second order. But portal doesn't compute this rate. Metabase query needed across two consecutive orders per user.
Q27a | Growth | Subscription Adoption Rate | NEW | ADD | Show % of active users with subscribtion_id IS NOT NULL vs total active users, by month. | orders table | COUNT(DISTINCT user_id WHERE subscribtion_id IS NOT NULL)/COUNT(DISTINCT active_user_id) × 100 | YES | 🔴<5% 🟡5–15% 🟢>15% | CMO | subscribtion_id field confirmed in orders API. Not tracked anywhere in portal. | Not surfaced in any portal page — DB field only | PORTAL-SKIP | No portal page reports on subscription adoption. Metabase query needed directly on orders table filtering subscribtion_id IS NOT NULL.
Q27b | Growth | Community Order Rate | NEW | ADD | Show % of orders where is_community_order=1, by zone and month. | orders table | COUNT(is_community_order=1)/COUNT(total_orders) × 100 per zone per month | YES | Track growth — baseline first | CMO | is_community_order and community_id confirmed in API. Community Pricing Master exists. | Masters → Community Pricing Master Create and manage community pricing tiers | PORTAL-ADAPT | Community Pricing Master exists for configuration. But no analytics page tracks community order volume or rate. Metabase query on is_community_order field needed.
Q28 | Finance | Gross Revenue (Daily / MTD / YTD) | KEEP | — | Show SUM(gross_revenue) as 3 KPI cards: today, MTD, YTD. Plus daily bar chart last 30 days. | v_daily_store_summary | SUM(gross_revenue) filtered by DATE, current_month, current_year | YES | Alert if daily <80% of target | Finance Head | Revenue Dashboard API confirmed. Date-null bug = ₹0 cards — tech must fix. | Revenue Dashboard → Total Revenue card + Completed/Ongoing Revenue cards Analytics → Store Revenue Details Business Overview: Overall Revenue ₹450,628 ↓25.7% | PORTAL-USE | Revenue Dashboard shows Total Revenue, Completed Revenue (₹3,86,69,88), Ongoing Revenue (₹62,379). Store Revenue Details has Business Overview with revenue + comparison to prev period. Use directly. Fix date-null bug first.
Q29 | Finance | Net Revenue Per Store | UPDATE | FORMULA EXPANDED | Show gross_revenue minus ALL 5 discount fields by zone_id and month. | v_daily_store_summary + orders (discount fields) | gross_revenue−(wallet+promo+cashback+voucher+coins) per zone per month | YES | Alert if net margin <70% of gross | Finance Head | All 5 discount fields confirmed. Wallet (₹1.54L utilised) was missing from original. | Analytics → Store Revenue Details Store-wise Revenue Trend chart (financial performance per hub) Revenue & Ops Hub → Store Wise Revenue card | PORTAL-ADAPT | Store-wise Revenue Trend shows gross revenue per store. But NET revenue (after discounts) is not computed in portal. Metabase subtracts all 5 discount fields.
Q30 | Finance | Average Order Value (AOV) | KEEP | — | Show SUM(order_amount)/COUNT(completed_orders) by zone and month. Trend line 6 months. | orders table | SUM(order_amount)/COUNT(finalorderstatus IN ('delivery-delivered','DELIVERED')) | YES | 🔴<₹250 🟡₹250–₹350 🟢>₹350 | Finance Head | Both finalorderstatus values confirmed in API — must include both. | Revenue Dashboard → Avg Order Value ₹196 ↓1.3% Prev ₹198.98 Analytics → Business Overview: Avg Order Value card Dashboard → Avg Order Value card | PORTAL-USE | AOV is one of the most-surfaced KPIs in portal — Revenue Dashboard (₹196), Analytics Business Overview, main Dashboard. Already available. Metabase adds zone-level breakdown and 6-month trend.
Q31 | Finance | Payment Mode Split | UPDATE | VALUE FIX | Show COUNT orders by payment_mode for current month. Donut chart. Use 'Cash' not 'COD'. | orders table | COUNT(*) GROUP BY payment_mode (Cash, Online) per month | YES | Alert if COD >60% | Finance Head | CRITICAL: payment_mode='Cash' not 'COD'. Silent data error in original. | Revenue Dashboard → COD Revenue ₹2,33,646 vs Online Revenue ₹4,692 Analytics → Online vs COD Order Trend + Online vs COD Revenue Trend charts | PORTAL-USE | Revenue Dashboard shows COD vs Online revenue split clearly. Online vs COD trend charts exist in Analytics. Use these directly. Metabase adds order COUNT split (not just revenue split).
Q32 | Finance | Total Discount Cost as % of Revenue | UPDATE | FORMULA EXPANDED | Show SUM of ALL 5 discount fields per month as % of gross_revenue. | orders table | SUM(wallet+promo+cashback+voucher+coins)/SUM(gross_revenue) × 100 | YES | 🔴>20% 🟡12–20% 🟢<12% | Finance Head | wallet_used (₹1.54L) was missing from original. All 5 confirmed. | Reports → Wallet History Report Cards: Money Wallet, Reward Wallet, Recharge, Referral, Order Refund, Partial Refund, Reward Voucher, Ticket Refund Revenue & Ops Hub → Wallet Overview (Live Balance & Transaction Stats) | PORTAL-ADAPT | Wallet History Report shows all wallet transaction types. Offer Report shows promo/cashback. But no single view aggregates ALL 5 discount types as % of revenue. Metabase computes this consolidated view.
Q33 | Finance | Razorpay Capture Rate | FLAG | DATA GAP | BLOCKED: razorpay_status=null for most records. Fix reconciliation first. | orders table | COUNT(razorpay_status='captured')/COUNT(payment_mode='Online') × 100 | PARTIAL | 🔴<95% 🟡95–98% 🟢>98% | Finance Head | razorpay_status NULL in API. Reconciliation flow broken per data readiness doc. | Revenue Dashboard → Online Revenue ₹4,692 (very low vs COD ₹2,33,646) Recent Transactions table in Revenue Dashboard | PORTAL-ADAPT | Revenue Dashboard has Recent Transactions table — shows individual transactions. Online Revenue is only ₹4,692 vs ₹2.33L COD — either online barely used or capture rate is broken. Verify with tech team.
Q34 | Finance | Refund Leakage (Total & Per Ticket) | UPDATE | RENAME + EXPAND | Show SUM(refund_amount) per month. Also AVG per ticket and refund % of gross revenue. | complaint_refund API (/api/get_complaint_refund_trend_details) + wallet_analytics (/api/wallet-analytics) Both confirmed. wallet-analytics returns: total_refund, total_ticket_refund, total_recharge, total_reward_voucher | SUM(refund_amount) AND SUM/COUNT = avg_refund_per_ticket | YES | 🔴refund >2% of revenue 🟡1–2% 🟢<1% | Finance Head | Renamed from 'Refund Cost'. Added revenue % threshold. | Complaint Management → Complaint Refund Report Table: Refund By, Complaints, Total Refund (₹), Promos Used/Not Used, Avg Refund Complaint Analytics → Complaints vs Refunds chart | PORTAL-USE | CONFIRMED: Two sources available: 1. /api/get_complaint_refund_trend_details — complaint-driven refunds with trend over months 2. /api/wallet-analytics — total_refund + total_ticket_refund financial fields Use (1) for trend chart, (2) for rupee total card. Both working per Bala SR audit.
Q35 | Finance | Revenue Per Zone (Ranked) | KEEP | — | Show SUM(gross_revenue) by zone_id for current month. Ranked horizontal bar chart. | v_daily_store_summary | SUM(gross_revenue) GROUP BY zone_id ORDER BY SUM DESC | YES | Top 3 green / Bottom 3 red | Finance Head | Store-wise revenue API confirmed. | Revenue & Ops Hub → Store Wise Revenue card Analytics → Store Revenue Details → Store-wise Revenue Trend (all 18 stores) Detail Order Analytics → Store Performance Analysis (18 stores with order counts) | PORTAL-USE | Store Performance Analysis in Detail Order Analytics shows all 18 stores with order counts and % growth (e.g. PURSAIWAKKAM ↑71.3%, 2938 orders). Store-wise Revenue Trend shows revenue per hub. Use directly. Metabase adds revenue-based ranking.
Q36 | Finance | Subscription vs One-Time Revenue Split | UPDATE | RENAME + EXPAND | Show SUM(order_amount) for subscription vs non-subscription orders by month. Show % split. | orders table | SUM(order_amount WHERE subscribtion_id IS NOT NULL) vs SUM(WHERE subscribtion_id IS NULL) | YES | Track subscription revenue % growth MoM | Finance Head | Renamed. Shows if subscription gaining share of revenue. | Not directly surfaced in any portal page | PORTAL-SKIP | No portal page shows subscription vs one-time revenue split. Metabase query on subscribtion_id field needed.
Q36a | Finance | Wallet Balance Outstanding (Liability) | NEW | ADD | Show total money_wallet_balance + reward_wallet_balance outstanding. Financial liability card. | wallet_details API (/api/wallet-details) + wallet_analytics (/api/wallet-analytics) wallet-details: total wallet liability. wallet-analytics: total_recharge=3629 in sample period | money_wallet_balance + reward_wallet_balance = total_outstanding_liability | YES | Alert if outstanding >₹1,50,000 | Finance Head | Wallet API confirmed: money=₹80,021, reward=₹37,359, total=₹1,17,380 outstanding. Financial liability not tracked. | Revenue & Ops Hub → Wallet Overview (Live Balance & Transaction Stats) Reports → Wallet History Report → Money Wallet + Reward Wallet cards | PORTAL-USE | CONFIRMED: /api/wallet-details returns money_wallet and reward_wallet balances (total liability to customers = ₹1.17L confirmed). wallet-analytics returns transaction breakdown: total_recharge, total_referral, total_reward_voucher, total_refund, total_ticket_refund. Both APIs working per Bala SR audit.
Q37 | Management | Revenue Growth Rate (MoM) | KEEP | — | Show gross revenue per month for last 12 months. MoM % change. Line chart with annotations. | v_daily_store_summary | (Revenue_M − Revenue_M-1)/Revenue_M-1 × 100 | YES | 🔴<0% 🟡0–5% 🟢>5% MoM | Founder | Top-line business health. Revenue Dashboard API confirmed. | Analytics → Store Revenue Details → Business Overview Overall Revenue ₹450,628 ↓25.7% vs Prev ₹606,297 Store-wise Revenue Trend chart (Month/Year granularity) | PORTAL-USE | Business Overview shows current vs previous period revenue with % change (currently ↓25.7% — needs investigation). Store-wise Revenue Trend chart supports MoM view. Use directly for headline. Metabase adds 12-month rolling trend.
Q38 | Management | Customer Lifetime Value (LTV) | UPDATE | INTERIM FORMULA | Show AVG LTV from v_customer_lifecycle (to be built). Interim: AVG(total spend per user_id). | v_customer_lifecycle (future) / orders (interim) | AVG(SUM(order_amount per user_id)) per cohort month — interim | PARTIAL | Track growth — baseline first | Founder | v_customer_lifecycle not yet built. Interim formula on orders table. | Dashboard → Cohort Analysis User Retention Cohort: Apr 2026 users with return rates Analytics → Revenue vs Orders by Persona chart | PORTAL-ADAPT | Revenue vs Orders by Persona shows revenue contribution per loyalty tier — proxy for LTV by segment. Cohort table tracks retention. True LTV needs v_customer_lifecycle view. Use portal as qualitative proxy.
Q39 | Management | Active Customers MoM (New vs Returning) | KEEP | — | Show COUNT DISTINCT user_id per month last 12 months. Overlay new vs returning. | orders table | COUNT(DISTINCT user_id) per month, split first-time vs repeat | YES | Alert if returning <50% of total actives | Founder | Key business health split — returning > new = healthy retention. | Analytics → User Growth Details New vs Old Customer Revenue chart New vs Old User Clothes Volume chart New vs Old User Orders chart | PORTAL-USE | Multiple charts in Analytics show New vs Old Customer breakdown: Revenue, Clothes Volume, Orders all split by new vs returning. User Retention & Status Trend chart also exists. Use directly.
Q40 | Management | Store Performance Ranking (Composite) | UPDATE | WEIGHT ADJUSTMENT | Rank zones by composite: net_revenue(35%) + on_time_rate(35%) + order_volume(20%) + inverse_complaint_rate(10%). | v_daily_store_summary + v_sla_tracking + v_complaint_summary | RANK by weighted composite formula per zone | PARTIAL | Top 3 green / Bottom 3 red | Founder | SLA weight raised to 35% — service quality = brand promise. Was 30%. | Detail Order Analytics → Store Performance Analysis (18 stores, order volume + % growth) Revenue & Ops Hub → Store Wise Orders + Store Wise Revenue Complaint Analytics → Store Wise Category Analysis (complaint breakdown per store) | PORTAL-ADAPT | Three separate portal pages have pieces: Store Performance (orders), Store Wise Revenue, Store Wise Complaints. No single page combines them into a composite rank. Metabase builds the weighted composite. Portal pieces are the source data.
Q41 | Management | Customer Satisfaction Score | UPDATE | SOURCE CLARIFIED | Show AVG(rating) per month and zone. Also feedback rate = rated / total complaints. | TWO SOURCES: 1. order_reviews_analytics (/api/order-reviews-analytics) — avg_rating, total_reviews, star breakdown 2. user_complaint table — rating per complaint ticket Use (1) for primary CSAT card, (2) for complaint-context rating | AVG(rating WHERE rating IS NOT NULL) per zone per month | YES | 🔴<3.5 🟡3.5–4.2 🟢>4.2 (out of 5) | Founder | Renamed from 'NPS'. STEAMEE uses ratings not NPS. BALA AUDIT UPDATE: /api/order-reviews-analytics confirmed — sample shows avg_rating=5, total_reviews=40, five_star=40, one_star=0. Note: order reviews and complaint ratings are separate data streams. Recommend showing both: Order CSAT (5-star scale) + Complaint Resolution Rating. | Complaint Management → User Complaints table (rating field per ticket) Complaint Analytics → Staff Performance: Status vs TAT chart | PORTAL-ADAPT | CONFIRMED: /api/order-reviews-analytics?from_date=X&to_date=X&zone_id=X&rating=X returns summary.average_rating and per-review data. Sample: avg=5/5, 40 reviews, all 5-star. SEPARATE from complaint ticket ratings in user_complaint table. Build TWO cards: (a) Order Quality Score from reviews API, (b) Complaint Resolution Rating from complaint API.
Q42 | Management | Complaint Rate Per 100 Orders | KEEP | — | Show (COUNT complaints / COUNT completed orders) × 100 per month. Trend line. | user_complaint + orders | COUNT(complaints)/COUNT(completed_orders) × 100 | YES | 🔴>3 per 100 🟡1–3 🟢<1 | Founder | 573 total complaints confirmed. Benchmark <1 per 100 for service business. | Analytics → Complaint Lifecycle Analytics Cards: Total Tickets 573 ↑88.5%, Open 83, Escalated 8, Closed 477, Reopened 14 Complaint Analytics → Total Tickets card | PORTAL-ADAPT | Complaint Lifecycle shows ticket count (573) with MoM % change. But no comparison against order volume — rate per 100 orders not computed. Metabase divides by completed orders. Portal cards are good leading indicators.
Q43 | Management | Order Volume Growth (MoM) | KEEP | — | Show COUNT orders per month last 12 months. MoM % change annotation. | orders table | (Orders_M − Orders_M-1)/Orders_M-1 × 100 | YES | 🔴<0% 🟡0–5% 🟢>5% MoM | Founder | Volume growth separate from revenue growth reveals pricing vs volume dynamics. | Analytics → Detail Order Analytics Store Performance Analysis: all 18 stores with order count + MoM % growth Store-wise Order Distribution Trend (stacked bars over time) | PORTAL-USE | Store Performance Analysis shows per-store order counts and % growth vs prior period (e.g. PURSAIWAKKAM: 2938 orders ↑71.3%). Store-wise Order Distribution Trend shows stacked volume over time. Use directly. Metabase aggregates to total MoM.
Q44 | Management | Channel Mix (App vs Admin vs WhatsApp) | UPDATE | VALUE MAPPING FIX | Show COUNT orders by orderplacedby per month. Map: 0=App, 1=Admin, 2=WhatsApp. Stacked bar. | orders table | COUNT(*) GROUP BY orderplacedby per month. Map 0→App, 1→Admin, 2→WhatsApp. | YES | Alert if WhatsApp >30% — app engagement issue | Founder | Mapping documented for first time — must enforce at query level. | Not directly surfaced with this breakdown in portal | PORTAL-SKIP | No portal page shows the App vs Admin vs WhatsApp channel split by orderplacedby value. Metabase query needed with CASE WHEN mapping.
Q45 | Management | VIP Customer Retention Rate | UPDATE | FORMULA SOURCE FIX | Show is_vip=1 users ordering in current month vs prior month. Use orders table directly. | orders table (is_vip field) — NOT v_customer_lifecycle | COUNT(DISTINCT user_id WHERE is_vip=1 AND current_month order)/COUNT(is_vip=1 AND prior_month order) × 100 | YES | 🔴<80% 🟡80–90% 🟢>90% | Founder | CRITICAL FIX: is_vip=1 confirmed in orders API. v_customer_lifecycle not yet built. | Analytics → User Growth Details → Active User Personas chart Revenue by User Persona chart (loyalty segments) | PORTAL-ADAPT | Active User Personas chart shows active users by loyalty tier. Revenue by User Persona shows revenue contribution by segment. 'Value' segment likely = VIP. Portal shows persona split but not retention rate. Metabase computes retention %.
Q45a | Management | Audit Compliance Rate | NEW | ADD | Show (RESOLVED+CLOSED audit issues)/TOTAL × 100 per store per month. | audit/summary API + admin/audit-issues | COUNT(status IN ('RESOLVED','CLOSED'))/COUNT(total_audit_issues) × 100 | YES | 🔴<60% 🟡60–80% 🟢>80% | Founder | Audit Dashboard: OPEN=82, IN_PROGRESS=2, RESOLVED=2, CLOSED=3. 82 open audits — alarming. PORTAL LIVE UPDATE (14-May-2026): OPEN=81, IN_PROGRESS=2, RESOLVED=3, CLOSED=3. Total=89. 1 audit resolved since initial capture. Current compliance rate = 6/89 = 6.7%. Still alarming — 91% of issues unresolved. | Operation Management → Audit Dashboard Cards: Open Issues 82, In Progress 2, Resolved 2, Closed 3 Tabs: Store Issues, Bag Audit, Inventory, Assets Operation Management > Audit Dashboard > /api/audit/summary + /api/admin/audit-issues Live: {OPEN:81, IN_PROGRESS:2, RESOLVED:3, CLOSED:3} | PORTAL-USE | PORTAL-USE CONFIRMED: Audit Dashboard shows Open/In Progress/Resolved/Closed counts with store, auditor, issue type, remarks, status, images. API: /api/audit/summary returns JSON counts. /api/admin/audit-issues returns full table. Tabs: Store Issues ¦ Bag Audit ¦ Inventory ¦ Assets. LIVE COUNT: 81 open (as of 14-May-2026). Compliance = 6.7%.
DEL1 | All | Ongoing Revenue (Standalone KPI) | REMOVE | MERGE | Merge into Q28 Gross Revenue card as sub-number. | v_daily_store_summary | N/A | N/A | N/A | N/A | ongoing_revenue appeared on Dashboard, Revenue Dash, Order Analytics as separate KPI cards. | Revenue Dashboard → Ongoing Total Revenue ₹62,379 card Analytics → Completed vs Ongoing Revenue chart | PORTAL-SKIP | Exists in portal as standalone card and chart. Decision: MERGE into Q28 display. Completed vs Ongoing Revenue chart can remain as visual breakdown — not a separate KPI.
DEL2 | All | Completed Revenue (Standalone KPI) | REMOVE | MERGE | Merge into Q28 Gross Revenue card. | v_daily_store_summary | N/A | N/A | N/A | N/A | Same duplication as DEL1. | Revenue Dashboard → Completed Total Revenue ₹3,86,6988 card | PORTAL-SKIP | Merge into Q28. Keep completed/ongoing split as a sub-breakdown within the revenue card, not a separate KPI card.
DEL3 | All | Cloth Revenue / Bag Revenue (Separate KPIs) | REMOVE | MERGE | Fold into Q31 Payment Mode Split as order_type dimension. | orders table | N/A | N/A | N/A | N/A | Cloth and Bag revenue split should be a dimension, not a standalone KPI. | Revenue Dashboard → Total Cloth Revenue ₹2,36,088 + Total Bag Revenue ₹2,250 Analytics → Cloth and Bag Revenue Trends chart | PORTAL-SKIP | Revenue Dashboard shows Cloth vs Bag Revenue split. Decision: MERGE into Q31 as an order_type filter. Cloth/Bag Revenue Trends chart in Analytics can stay as a visual — not a separate KPI.
DEL4 | All | User Returning (Standalone Page/KPI) | REMOVE | MERGE | Absorb into Cohort Analysis as a tab. | orders + users | N/A | N/A | N/A | N/A | Identical API to Cohort Analysis. Confirmed duplicate. | User Management → User Returning (Cohort cards + returning table) Dashboard → Cohort Analysis | PORTAL-SKIP | User Returning page has same cohort metrics as Cohort Analysis page. Decision confirmed: merge User Returning as tab inside Cohort Analysis. Remove standalone nav entry.
DEL5 | All | Complaint Analytics (Dashboard Tab) | REMOVE | MOVE | Move to Complaint Management. Dashboard shows summary badge only. | user_complaint | N/A | N/A | N/A | N/A | Complaint Analytics belongs to the team resolving complaints, not Dashboard home. | Dashboard → Analytics → Complaint Lifecycle Analytics section Complaint Management (no analytics sub-page yet) | PORTAL-SKIP | Complaint Lifecycle Analytics section is currently in the Dashboard Analytics panel. Decision: MOVE to Complaint Management as a sub-page. Dashboard keeps only total ticket count badge.
DEL6 | All | Analytics (Dashboard sub-item) | REMOVE | CONSOLIDATE | Delete duplicate Analytics sub-item. Keep standalone Analytics entry. | N/A | N/A | N/A | N/A | N/A | Exact duplicate confirmed — Dashboard→Analytics and standalone Analytics sidebar call identical APIs. | Dashboard → Analytics sub-item (duplicate) Sidebar → Analytics (standalone — keep this one) | PORTAL-SKIP | Navigation duplication confirmed in Analysis doc (Sheet2: 'Exact duplicate of standalone Analytics sidebar entry'). Remove Dashboard sub-item. Keep standalone sidebar entry.
PORTAL STATUS LEGEND → | PORTAL-USE | Portal page already has this data — use directly | PORTAL-ADAPT | Portal has partial data — needs Metabase formula on top | PORTAL-SKIP | Not in any portal page — Metabase query needed from scratch

## BUGS & DATA GAPS
ID | Type | Location | Issue | Impact on KPIs | Priority | Action Required
B1 | BUG | Analytics API /metrics/data | 'other_orders' field returns -151. Arithmetic error in order state reconciliation — negative order count. | Any KPI counting order states will be wrong. Q5, Q9, Q43 affected. | P0 — CRITICAL | Tech team must audit order_status arithmetic. Sum of order states must equal total_orders. Fix before any KPI dashboard goes live.
B2 | BUG | Revenue Dashboard /revenueDashboard | Without date filter, API returns total_order_value=₹0, cloth=₹0, bag=₹0, AOV=₹0 despite showing completed_revenue=₹24.69L. Date-unfiltered response is partially broken. | Q28, Q30, Q36 will show ₹0 cards if date filter not passed by frontend. | P0 — CRITICAL | Backend must return sensible defaults (MTD) when no date filter passed. Frontend must enforce date param in all revenue API calls.
B3 | BUG | Order Reviews Report /Iron/public/OrderReviews | Hard SQL error — page completely broken. Table returns ERROR state. | Any KPI requiring review/rating data from this page is unavailable. | P1 — HIGH | Remove from sidebar nav until fixed. Tech team to debug SQL query. Expected behaviour: list of order reviews with rating, text, date.
B4 | BUG | Dashboard Filter /Iron/public/home | Main dashboard filter returns HTTP 500 Internal Server Error when date range applied. | ALL date-filtered KPI cards on main dashboard are blind. Q1–Q9 on dashboard home are unreliable. | P0 — CRITICAL | Fix filter endpoint. This is the most-used page — all KPI cards depend on date filtering working.
B5 | BUG | Onboarding Report /user-report | finalorderstatus filter uses 'delivery-delivered' AND 'DELIVERED' — both string values in use. Inconsistent enum. | Q20 (new customers), Q38 (LTV interim) will miss orders if only one status value queried. | P1 — HIGH | Standardise finalorderstatus to single enum. Until fixed, all queries must include BOTH: WHERE finalorderstatus IN ('delivery-delivered', 'DELIVERED').
G1 | GAP | marketing_spend table | No channel-level marketing spend table exists anywhere in the database. | Q22 (CAC) completely blocked. Cannot compute customer acquisition cost per channel. | P2 — PHASE 2 | Create marketing_spend table: (id, date, channel, campaign_name, spend_amount, new_users_attributed). Manual entry or MoEngage integration.
G2 | GAP | Push notification tracking | Open rates and conversion rates from push notifications are not tracked in DB. | Campaign effectiveness measurement impossible. MoEngage ROI cannot be proven. | P2 — PHASE 2 | Implement MoEngage event tracking first. Pass app_opened and campaign_click events to DB.
G3 | GAP | Razorpay reconciliation | razorpay_status is NULL for most online orders. Reconciliation flow 'not functioning properly' per data readiness doc. | Q33 (Razorpay Capture Rate) will show inflated failure rate or require manual cross-check. | P1 — HIGH | Fix Razorpay webhook to update razorpay_status on capture event. Build reconciliation view joining orders.transaction_id to Razorpay API response.
G4 | GAP | Pressman payout table structure | Payout tracked but 'needs proper formatting of report' per data readiness. | Pressman Productivity Score (Q9b) cost component cannot be automated. | P1 — HIGH | Structure payout table: (ironer_id, date, order_count, cloth_count, payout_amount). Ironer Performance Report API exists — payout must be added as field.
G5 | GAP | DATETIME fields on orders | picked_up_time, deliveryto_ven_time, ironstart_time, ironend_time are NULL in most records per API audit. | Q18 (Pickup-to-Store Time), Q4 (E2E TAT) are partially blocked. SLA views depend on these timestamps. | P0 — CRITICAL | Verify mobile app is writing timestamps at each stage transition. If app is writing them, DB trigger or API is swallowing them. Timestamps are the backbone of every SLA KPI.
G6 | GAP | v_sla_tracking and v_daily_store_summary views | KPI framework references these SQL views but it's unclear if they exist in current DB schema. | Q1–Q5, Q14–Q15, Q28–Q29, Q35 all source from these views. | P0 — CRITICAL | Tech team must confirm these views exist or create them. Provide view definitions to tech team as part of Metabase spec delivery.
G7 | GAP | v_customer_lifecycle view | Q26, Q38, Q45 reference v_customer_lifecycle. Not confirmed to exist. | LTV (Q38), Churn Rate (Q26), VIP Retention (Q45) partially blocked. | P1 — HIGH | Create view: v_customer_lifecycle (user_id, first_order_date, last_order_date, total_orders, lifetime_value, churn_status, segment_name). Can be derived from orders + users tables.
B6 | BUG | Order Reviews Report SQL Error | Order Reviews Report page returns hard SQL error — page completely broken. Confirmed in SUMMARY sheet bug log. | Q41 (Customer Satisfaction Score) partially blocked. Order review data unreachable via portal page. API /api/order-reviews-analytics still works directly. | P1 — HIGH | Fix SQL error on Order Reviews page. Until fixed, pull rating data via /api/order-reviews-analytics directly in Metabase. Do not rely on portal page view.
G8 | NOTE | Avg Delivery Time unit ambiguity | Rider Performance API returns avg_delivery_time=136.8. Unit not documented — likely minutes but could be seconds. | Q3 (On-Time Delivery Rate), Q12 (Deliveries Per Rider), Q10 (Rider Utilisation) may show wrong scale if unit is wrong. | P1 — HIGH | Tech team to confirm unit of avg_delivery_time in /api/rider-performance-analytics. If minutes: 136.8 min = 2.28 hrs per delivery — that is high, verify. If seconds: 136.8s = 2.28 min — likely wrong. Clarify and document in API spec.

## CLIENT HANDOFF
STEAMEE — KPI Change Summary for Client Presentation
🟢 NEW KPIs (11 Added)
Q# | KPI Name | Dashboard | Key Change / Why
Q9a | Slot Utilisation Rate | Operations | Slot capacity vs demand heatmap — drives rider pre-positioning
Q9b | Pressman Productivity Score | Operations | Clothes ironed per shift vs benchmark — ironer scorecard
Q9c | Inventory Stock-Out Alerts | Operations | Low-stock badge count per store — prevents production stoppages
Q18a | Rider Attendance Rate | Logistics | % riders showing up on time — direct SLA breach predictor
Q27a | Subscription Adoption Rate | Growth | % active users on subscription plan — LTV multiplier
Q27b | Community Order Rate | Growth | % orders via community pricing — growth lever, never tracked
Q36a | Wallet Balance Outstanding | Finance | Total wallet liability (₹1.17L confirmed) — financial exposure
Q45a | Audit Compliance Rate | Management | Open audit resolution % — 81 open audits (live: 14-May-2026) found, never in framework
DEL→ | Promo-to-Organic Retention Rate | Growth | (Renamed + improved Q27 — measures habit formation post-promo)
DEL→ | Smart Bag Utilisation Rate | Growth | (Renamed Q25 — 'Smart Bag' is the product name)
DEL→ | Refund Leakage | Finance | (Renamed Q34 — expanded to include refund % of revenue)
🔵 UPDATED KPIs (9 Changed)
Q# | KPI Name | Dashboard | Key Change / Why
Q10 | Rider Utilisation Rate | Logistics | Source: use Rider Performance Report API (not time mgmt timestamps)
Q13 | COD Collection Rate | Logistics | Field fix: payment_mode='Cash' NOT 'COD' — was returning wrong data
Q15 | Rider-Caused Delay Rate | Logistics | Denominator: total orders (not just breached orders) — honest rate
Q23 | Promo ROI | Growth | Now aggregates all 5 discount fields: wallet+promo+cashback+voucher+coins
Q24 | App Funnel Conversion Rate | Growth | Source: use Onboarding Report API conversion_rate field directly
Q29 | Net Revenue Per Store | Finance | Formula: all 5 discount fields subtracted, not just total_discount
Q31 | Payment Mode Split | Finance | CRITICAL: payment_mode='Cash' not 'COD' — fix prevents silent data error
Q32 | Total Discount Cost % | Finance | Now includes wallet_used (₹1.54L) — was missing from formula
Q44 | Channel Mix | Management | orderplacedby mapping enforced: 0=App, 1=Admin, 2=WhatsApp
🔴 REMOVED / MERGED KPIs (6 Eliminated)
Q# | KPI Name | Dashboard | Key Change / Why
DEL1 | Ongoing Revenue (standalone) | All dashboards | Merged into Q28 Gross Revenue card as sub-number
DEL2 | Completed Revenue (standalone) | All dashboards | Merged into Q28 Gross Revenue card as sub-number
DEL3 | Cloth / Bag Revenue (separate KPIs) | All | Merged as order_type dimension in Q31 Payment Mode Split
DEL4 | User Returning (standalone page) | User Mgmt | Absorbed into Cohort Analysis — identical API, confirmed duplicate
DEL5 | Complaint Analytics (Dashboard tab) | Dashboard | Moved to Complaint Management — Dashboard shows badge count only
DEL6 | Analytics (Dashboard sub-item) | Dashboard nav | Removed — exact duplicate of standalone Analytics sidebar entry
⚠️ FLAGGED KPIs — Data Not Ready (7)
Q# | KPI Name | Dashboard | Key Change / Why
Q22 | CAC by Channel | Growth | BLOCKED: marketing_spend table does not exist — Phase 2
Q33 | Razorpay Capture Rate | Finance | PARTIAL: razorpay_status=null for most records — fix reconciliation first
Q18 | Avg Pickup-to-Store Time | Logistics | PARTIAL: picked_up_time NULL in most orders — verify app timestamps
Q38 | Customer LTV | Management | PARTIAL: use interim orders formula until v_customer_lifecycle built
G5 | DATETIME fields on orders | ALL | picked_up_time, ironstart_time, ironend_time NULL — SLA views blocked
G6 | v_sla_tracking view | Ops/Logistics | Must be created by tech team — 8 KPIs depend on it
G7 | v_customer_lifecycle view | Growth/Mgmt | Must be created by tech team — 3 KPIs depend on it

## LEGEND
COLOUR & STATUS LEGEND
Status | Meaning
KEEP | KPI unchanged — formula and source validated
NEW | New KPI added to framework
UPDATE | Existing KPI modified — formula, source, or naming changed
REMOVE | KPI eliminated or merged into another
FLAG | KPI exists but data is not ready — Phase 2 or tech fix needed
Change Type | Meaning
ADD | New KPI, not in original list
FORMULA FIX | Formula was incorrect or imprecise
SOURCE FIX | Wrong table/field referenced in original
DATA GAP | Blocked by missing data infrastructure
MERGE | Duplicate KPI consolidated into another
MOVE | KPI moved to more appropriate dashboard
— | No change

## NEW APIS REQUIRED
API Endpoint | Purpose | Target KPIs / Client Metrics | Required Data Fields | Priority | Implementation Notes
/api/stock-inventory | Track daily opening stock, closing stock, stock receipts, and stock usage at each store. | Opening/Closing stock quantity, Stock daily usage, Stock receipts (Stock Category - P0) | store_id, date, opening_qty, closing_qty, stock_received_qty, stock_used_qty, stock_type_id | P0 - CRITICAL | Required for daily operational compliance. Feeds stock alerts and helps reconcile chemical/bag usage against actual orders processed.
/api/delayed-orders | List all active orders that have exceeded the SLA threshold (24 hours) in any stage. | Delayed orders marking - delivery pending / ironing pending >24hrs (Store Wise Category - P0) | order_id, store_id, current_status, time_in_status_hours, customer_name, customer_phone | P0 - CRITICAL | Operational flag. Surface delayed bags directly on store manager's overview so they can escalate immediately before SLA breaches.
/api/order-inventory | Real-time list of bags and orders physically present in the store (received vs delivery pending). | Store wise received bags, Store wise delivery pending bag lists (Order Inventory - P0) | store_id, bag_barcode, order_id, status (received/ironing/completed), received_date, rack_location | P0 - CRITICAL | Surfaces bag physical audit status. Reconciles app orders with actual bags sitting on racks.
/api/machine-maintenance | Track machine downtime hours, maintenance service costs, and cleanliness compliance checklist. | Machine downtime in Hrs, Machine service cost, Cleanliness compliance % (Machine Maintenance - P1) | store_id, machine_id, downtime_start, downtime_end, repair_cost, cleanliness_score, inspector_id | P1 - HIGH | New schema table required. Standardizes store operations audit and monitors machine breakdown overheads.
/api/pincode-analytics | Analyze customer orders, sales, promocodes, and complaints on a granular geospatial pincode level. | Pincode based customers, pincode based sales, promocode expense, orders, complaints (Pincode - P1) | pincode, zone_id, active_customers_count, gross_sales_value, promocode_discount_value, order_count, complaints_count | P1 - HIGH | Crucial for localized marketing spend and determining which areas require cluster pricing or dedicated store allocation.
/api/marketing-attribution | Reconcile customer acquisition channels (organic, Facebook, Google ads) with marketing spend and customer lifecycle status. | Effective marketing split, CAC per store, downloads vs active customers (Marketing Category - P2) | date, store_id, channel (FB/Google/Referral), spend_amount, downloads_count, active_cust_acquired | P2 - PHASE 2 | Blocked by G1/G2 (missing marketing spend table). Once spend is tracked, this API calculates real CAC by store.
/api/invoicing | Auto-generate bills or invoices for completed orders with detailed splits. | Creating invoice or bills based on orders (Accounting Category - P2) | order_id, billing_details, gross_amount, discounts_applied, tax_amount, net_payable_amount, invoice_pdf_url | P2 - PHASE 2 | Integrate with a standard PDF generation library and log transaction states in DB for compliance.
/api/get_mau_split_trend | Tracks referral code virality loops and conversion rates without new tables. | [SUGGESTION] Referral Virality K-Factor (Growth - P2) | referral_code, referred_by, created_at, orders_placed | P2 - PHASE 2 | Uses existing referrals database columns to calculate user sharing ratios.
/api/get_booking_pattern_trend | Segments user order counts and billing totals based on household size (family_count). | [SUGGESTION] Household Size vs AOV (User Analytics - P1) | family_count, order_id, gross_amount, quantity | P1 - HIGH | Leverages existing user family count metadata for target marketing split.